STREETNOTES.AI

APRIL 2026  |  CONFIDENTIAL

Validated Strategy

& Restructured GTM

Moat Assessment. Aesthetics Vertical Lock-In.

The Path to 7/10.

Prepared for

Jeff Meyers

Michael Hervis

Co-Founders

# Executive Summary

This document serves three purposes: validate the existing moat plan against the aesthetics vertical brief, identify the specific adjustments required, and restructure the 90-day Blitzkrieg GTM into a 24-month sequence that matches how the aesthetics market actually concentrates.

### The Three Findings

1. The moat plan is strategically sound. Reframe, sub-vertical discipline, concierge onboarding, founder-led category creation, 10-dimension moat framework — all validated. Keep them. The spine of the strategy does not change.

2. The vertical choice is wrong. Aesthetics beats medical devices. Michael's Symplast network, AmSpa community density, the Veeva migration window, and the $29B→$97B trajectory together make aesthetics the superior beachhead. The smaller TAM is the advantage — it is ownable in 18 months.

3. The Blitzkrieg fires in Month 12, not Day 90. Detonation Day is postponed, not killed. Spend $10K-15K proving the aesthetics model. Then $20K-40K scaling inside the vertical. Then $50K-130K detonating into the broad market — with aesthetics case studies as the proof that makes the spend work.

### The Revised Moat Score

The aesthetics pivot lifts the weighted moat score from ~7.2/10 (moat plan target) to ~7.5/10. Four dimensions improve, one declines slightly, five are unchanged. Details in Section 1.4.

### The Single Metric

Referral rate. If aesthetic reps are not telling other aesthetic reps within the first 90 days of paid adoption, the moat is not forming and the sequencing must be reassessed.

### Document Roadmap

| Part | Focus | Pages |
| --- | --- | --- |
| 1 | Moat plan validation, five required adjustments, revised moat score | 3-8 |
| 2 | Restructured three-phase GTM, detailed Phase 1 timeline, budget comparison | 9-16 |
| 3 | The six competitive moats (3 existing, 2 inherited, 1 new) | 17-18 |
| 4 | Metrics, leading/lagging indicators, moat score trajectory | 19-20 |
| 5 | Critical files to modify, prioritized by phase | 21 |

# Part 1 — Moat Plan Validation

This document validates the existing moat plan against the aesthetics vertical brief, identifies five specific adjustments required, and restructures the 90-day Blitzkrieg GTM into a 24-month sequence that matches how the market actually concentrates.

## 1.1 — Assessment Verdict

The moat plan is STRONG. One of the best strategic documents I have reviewed for a pre-revenue SaaS. The core thesis is correct and five of its most important calls are validated against independent research: - "Stop calling this voice-to-CRM" — VALIDATED. Competitive intelligence confirms Hey DAN (pure voice-to-CRM) shows 1.7K monthly visits declining 34.6%. The category is a feature, not a business. The Field Intelligence Platform reframe is the right move. - "Pick one sub-vertical" — VALIDATED. Every durable vertical SaaS (ServiceTitan, Toast, Procore, Veeva) followed this path. The moat plan's case studies are accurate and well-applied. - "Concierge onboard the first 200" — VALIDATED. Superhuman's playbook. Linear's first customers. This is how the switching-cost layer the moat plan describes actually gets built. - "Jeff as category creator" — VALIDATED. Twenty-five years, eleven President's Clubs, and a sales background are non-replicable assets. The publishing play is the right distribution bet. - "The 7.2/10 weighted score is achievable in 18-24 months" — MOSTLY VALIDATED, with the caveats in Section 1.3.

## 1.2 — What the Moat Plan Gets Right (Keep As-Is)

Eleven structural choices in the moat plan should not be changed. They form the spine of the strategy and every adjustment below preserves them.

- The big reframe — "Field Intelligence Platform," not voice-to-CRM.

- The competitive reality matrix — accurate and well-researched.

- The 10-dimension moat scoring framework.

- The "what to explicitly stop doing" section — every item is correct.

- The phase-gated 18-month structure.

- The switching-cost foundation — user_field_rules, per-rep voice style learning.

- The cross-user data flywheel concept.

- The integration-depth wave plan.

- The metrics framework — referral rate as the single metric to watch.

- The "where this plan breaks" honest-assumptions section.

- The disciplined sequencing of product investments against distribution proof.

## 1.3 — Where the Moat Plan Needs Adjustment

Five adjustments. Each preserves the moat plan's structure while correcting a specific choice that the aesthetics investor brief exposes as suboptimal.

### Adjustment 1 — The vertical choice is wrong. Aesthetics beats medical devices.

The moat plan recommends medical device sales (surgical and implant reps). That was the right call with the data available at the time. The aesthetics investor brief reveals a superior vertical choice for the reasons in the table below.

| Dimension | Medical Devices | Aesthetics | Winner |
| --- | --- | --- | --- |
| TAM | ~50K reps | ~3,000-6,000 reps | Med devices (but too big to dominate fast) |
| Competitive density | Empty (good) | Completely empty (better) | Aesthetics |
| Founder access | Moderate — enterprise SaaS network has device vendor ties | Michael Hervis ran VP-level ops at Symplast; has direct relationships with aesthetic brand VPs | AESTHETICS (massive advantage) |
| Community concentration | Dispersed across specialties | One organization (AmSpa, 9,000+ members), one conference | AESTHETICS |
| Workflow fit | Extreme — reps live in hospitals | Equally extreme — 60% of day driving; track multiple injectors per practice | Tie |
| CI intensity | High (Stryker vs Zimmer vs Medtronic) | Extreme (Allergan vs Galderma vs Merz vs Revance — brand war is the daily workflow) | Aesthetics |
| Price tolerance | $99-299/seat justified | $199/seat < a single physician dinner. Non-conversation. | Tie |
| Speed to dominance | 50K reps = years to "own" | 3,000-6,000 reps = ownable in 18 months | AESTHETICS |
| Market trajectory | Mature | $29B (2025) → $97B (2035), 12.76% CAGR [1]; MedSpa locations 9,000 → 12,000+ by 2027 | AESTHETICS |
| Competitive window | Always open | Veeva mid-migration (stability mode since Dec 2023; accelerated cutoff Dec 2029) [4]. 18-month window. | AESTHETICS |

The smaller TAM is the advantage. The moat plan itself says "pick a vertical so narrow it sounds embarrassing." Medical devices at 50K reps is too big to dominate quickly. Aesthetics at 3,000-6,000 reps is ownable. The entire market is reachable through one conference (AmSpa Medical Spa Show — 9,600+ attendees) and one co-founder's network (Michael at Symplast).

### Adjustment 2 — Budget must scale DOWN, not up.

The Blitzkrieg plan allocated $130K-153K (Full Blitz) or $38K-40K (Lean Blitz) for broad-market saturation. The aesthetics pivot makes those budgets wrong in both directions.

- $130K is wasteful — you do not need LinkedIn ads targeting 200K+ job titles when your market is 5,000 people reachable through warm relationships and one conference.

- $38K is also wrong — but the $10K-15K budget in the investor brief is right-sized for density-based distribution in a concentrated market.

The investor brief's budget breakdown is correct: attend the conference, host the dinner, work the warm network, concierge onboard, let referrals compound. In a 5,000-person market, this beats every paid channel.

### Adjustment 3 — The 90-day north star becomes 20 reps, not 50 teams.

The Blitzkrieg plan targeted 50 teams by Day 90 across a broad market. With aesthetics the targets compress into a tighter, denser cohort:

- Month 1: 5-10 pilot conversations at brand level + 20 individual rep conversations.

- Month 2: 10-15 paying reps, conference presence established.

- Month 3: 20-30 paying reps, first brand team deployment (5+ seats).

These numbers look "smaller" but represent 0.5-1% market penetration in a concentrated vertical. That is more dominant than 50 scattered teams across all of field sales.

### Adjustment 4 — The Blitzkrieg's "Detonation Day" gets postponed, not killed.

The Simultaneous Detonation concept is brilliant but premature for the aesthetics beachhead. The right sequence:

- Months 0-6: Aesthetics beachhead via investor brief playbook (dark build + founder-led sales + concierge onboarding). No public detonation.

- Months 6-12: Team expansion and CI wedge within aesthetics. Begin building Detonation Day assets.

- Month 12+: DETONATION when expanding to the second vertical (enterprise SaaS AEs or medical devices). Broad-market awareness matters then. The aesthetics beachhead is proof, not the launch.

### Adjustment 5 — The moat plan underweights Story Vault.

The moat plan barely mentions Story Vault. The investor brief does not mention it at all. But Story Vault is the retention and viral engine:

- "How I handled the surgeon who preferred Competitor X" → in aesthetics: "How I handled the injector who was loyal to Allergan when I'm selling Revance."

- Team-vs-team Story Vault challenges create the network effect the moat plan scores at 2/10 today.

- "Beat My Score" gamification creates organic sharing that compounds within the small community.

- The Team Vault becomes the single most valuable asset for new rep onboarding at any aesthetic brand.

Ship Story Vault in Phase 1, not Phase 2. Retention, virality, and community density all compound off this single artifact. Deferring it is the single costliest product sequencing mistake in the moat plan.

## 1.4 — Revised Moat Score with Aesthetics Vertical

The vertical pivot lifts the weighted moat score from ~7.2/10 to ~7.5/10. Four dimensions improve, one decreases slightly, five stay constant.

| Moat Type | Moat Plan Target | Revised (Aesthetics) | Change | Why |
| --- | --- | --- | --- | --- |
| Vertical lock-in | 8 | 9 | +1 | 5,000 reps = ownable. Medical devices at 50K was harder. |
| Distribution / founder | 9 | 10 | +1 | Michael's Symplast network is the single most undervalued asset. |
| Brand / category | 8 | 8 | Same | "Field Intelligence for Aesthetics" — own the term. |
| Switching costs | 8 | 8 | Same | Same mechanism; vertical-specific vocabulary makes it stickier. |
| Network effects (team) | 7 | 8 | +1 | Concentrated community = faster flywheel. Story Vault within brands. |
| Per-user data moat | 8 | 8 | Same | Same mechanism. |
| Integration depth | 7 | 6 | -1 | Fewer integrations needed initially (most aesthetic CRMs are simpler). |
| Cross-user data moat | 6 | 7 | +1 | Smaller population reaches critical mass faster. |
| UX / speed | 8 | 8 | Same | Same mobile-first obsession. |
| Proprietary tech | 3 | 3 | Same | Realistic ceiling unchanged. |
| Weighted Average | ~7.2/10 | ~7.5/10 | +0.3 | Aesthetics is the superior vertical for every moat dimension that matters. |

# Part 2 — The Restructured GTM Plan

Three-phase structure preserved from the moat plan. GTM mechanics completely restructured for aesthetics density.

## 2.1 — Strategy Summary

### Phase 1 — Months 0-6: Aesthetics Beachhead ($10K-15K budget)

Keep the investor brief's GTM exactly as written. It is the right playbook for this market. Additions:

- Ship Story Vault with aesthetic-specific content during this phase (not deferred).

- Begin "State of Aesthetic Field Sales" report by month 3.

- Jeff's LinkedIn content focuses on aesthetics workflow pain, not generic sales.

### Phase 2 — Months 6-12: Team Moat + CI Wedge ($20K-40K budget increase)

Keep the moat plan's Phase 2 product bets:

- Manager dashboard as first-class citizen.

- Dynamic battle cards (Allergan vs Galderma vs Merz positioning).

- Team-vs-team Story Vault challenges.

- Cross-user learning (opt-in).

- Free manager seat on team plans.

Distribution shifts:

- AmSpa membership + conference presence becomes the primary channel.

- "Aesthetic Field Intelligence Report" published quarterly (proprietary data only StreetNotes has).

- Narrow paid ads only if referral rate stalls: LinkedIn targeting aesthetic brand job titles (VP Sales at Revance, Galderma, Merz).

- Begin influencer seeding within aesthetic sales community (not broad sales influencers).

### Phase 3 — Months 12-24: Second Vertical + Detonation ($50K-130K budget)

THIS is when the Blitzkrieg fires. Not before.

- Second vertical: enterprise SaaS AEs or medical devices (Jeff's natural ICP).

- Detonation Day launches for the second vertical — with aesthetics case studies as proof.

- Blitzkrieg influencer strategy (Josh Braun, John Barrows, Morgan Ingram) activates here.

- The full ad budget makes sense now — the market is 200K+ reps, not 5,000.

- Product Hunt, AppSumo, podcast blitz — all timed for the broad-market launch.

- Aesthetics vertical continues to compound via community and referral.

## 2.2 — Detailed Phase 1 Timeline (Months 0-6)

### Month 1 — Founder-Led Outreach ($2,000-3,000)

Weeks 1-2

- Pick the vertical. Commit in writing. Update every artifact.

- Michael identifies 15-20 contacts at aesthetic brands (Revance, Merz, Galderma, Evolus, InMode).

- Michael sends warm intro emails + schedules 30-min calls.

- Jeff builds list of 300 individual aesthetic reps on LinkedIn.

- Ship vertical-specific extraction prompts (lib/notes/prompts.ts rewritten for aesthetics).

- Seed competitor alias dictionary: Allergan, Galderma, Merz, Revance, Evolus, InMode, BTL, Cutera, Sciton, Candela.

Weeks 3-4

- Jeff begins personalized LinkedIn DMs + emails to 300 reps.

- Rewrite /debrief lead magnet: "Post-Visit Debrief for Aesthetic Sales Reps."

- Ship CRM stage mapper for aesthetics: eval → trial → case coverage → committee review.

- Begin user_field_rules table (switching cost foundation).

Month 1 target 5-10 pilot conversations at brand level. 20+ individual rep conversations.

### Month 2 — Conference Presence ($4,000-5,000)

- Attend Aesthetic Next (Dallas, Sept 2026) or next AmSpa state event.

- Pre-book 15 coffee chats via LinkedIn.

- Host "Aesthetic Field Sales Confidential" dinner (30 people, $2-3K).

- Jeff as MC, 2 rep panelists, conversational format.

- Demo StreetNotes live at the dinner (not a pitch — a "watch this" moment).

- Ship Story Vault MVP with aesthetic content: "Injector Objection Handling," "Switching a Loyal Allergan Account," "MedSpa Grand Opening Pitch."

Month 2 target 50 conversations. 10 warm demos. 5-10 new paying reps.

### Month 3 — Concierge Onboarding + Referral ($2,000-3,000)

- Every new customer gets Jeff's 30-minute setup call.

- Configure CRM mapping, train aesthetic vocabulary, demonstrate pre-visit brief.

- Day 5-7: "You saved X hours this week. Know another rep? $500 credit."

- Ship per-rep voice style learning (corrections → remembered rules → writes in their voice).

- Publish first "State of Aesthetic Field Sales" micro-report (based on 10+ customer interviews).

- Begin "Beat My Score" Story Vault challenge within first paying teams.

Month 3 target 20-30 paying reps. First brand team deployment (5+ seats).

### Months 4-6 — Compound & Strengthen ($2,000-4,000)

- 60-second ritual push notification live (calendar integration → post-meeting prompt).

- Jeff's LinkedIn cadence: 3x/week posts on aesthetic field sales workflow.

- Manager dashboard alpha for brand-level team accounts.

- Dynamic battle cards v1 (Allergan vs Galderma vs Merz positioning).

- Cross-user learning opt-in (default on with disclosure).

- AmSpa membership for community access + credibility.

- First named case study published: "[Brand X] increased CRM completion from X% to Y%."

Months 4-6 target 50-100 paying reps. 80%+ 3-month retention. 3-5 team deployments.

## 2.3 — Budget Comparison

The aesthetics pivot does not save money long-term — it sequences the spend correctly.

| Phase | Original Blitzkrieg | Aesthetics-Optimized | Savings |
| --- | --- | --- | --- |
| Phase 1 (Months 0-6) | $65K-76K (half of Blitz) | $10K-15K | 80% less |
| Phase 2 (Months 6-12) | $65K-76K | $20K-40K | 50% less |
| Phase 3 (Months 12-24) | N/A (was 90-day plan) | $50K-130K (Blitzkrieg fires here) | Deferred, not eliminated |
| 24-Month Total | $130K-153K (in 90 days) | $80K-185K (in 24 months) | Spread across 24 months instead of 90 days |

The logic of the sequence Burn $10K-15K proving the model. Then $20K-40K scaling within the vertical. Then $50K-130K detonating into the broad market — with proof.

## 2.4 — What to Explicitly Stop Doing

### Preserved from the moat plan — all still correct

- Stop building adjacent surfaces (/vbrick, /ci as public dashboard).

- Stop treating "voice-to-CRM" as the positioning.

- Stop chasing "generic SMB to mid-market sales teams."

- Stop calling Gong a non-competitor.

- Stop saying "45 years of experience" is a moat.

- Stop shipping customizability.

### New additions from the aesthetics pivot

- Stop planning a $130K ad blitz for a 5,000-person market. Density beats scale here.

- Stop building for "field sales" generically. Every prompt, landing page, and demo should say "aesthetic reps."

- Stop deferring Story Vault. It is the retention engine and viral mechanic. Build it in Phase 1.

- Stop treating Michael's Symplast network as a nice to have. It is the distribution moat. Use it in Week 1.

## 2.5 — Operating Cadence

The restructured GTM only works if the operating cadence matches the phase. Weekly reviews should center on different questions at each stage.

| Phase | Weekly Review Question | Decision Triggered |
| --- | --- | --- |
| Phase 1 (0-6m) | How many aesthetic reps had a concierge onboarding call this week, and how many said "I need to tell [specific name]" unprompted? | If the unprompted name-drop rate is below 40%, pause outbound — product is not yet referral-worthy. |
| Phase 2 (6-12m) | What is the team-seat expansion ratio within brand accounts, and what is the Story Vault weekly active submission rate? | If submission rate < 30% of paid MAU, gamification is not working — ship "Beat My Score" improvements before Phase 3. |
| Phase 3 (12-24m) | Is the second vertical's Week 1 activation matching or beating aesthetics' Week 1 activation? | If not, verticalization assumption is wrong — pause second-vertical spend and reinvest in aesthetics depth. |

One meeting, one metric, one decision. Every Monday: one review, one leading indicator per phase, one explicit decision. The moat plan's biggest execution risk is calendar drift — Jeff and Michael defaulting to "update" meetings instead of "decision" meetings. Protect the cadence.

# Part 3 — The Competitive Moats

Three moats from the original moat plan. Two more from the Blitzkrieg plan. One new one — surfaced only by the aesthetics pivot.

### From the moat plan (preserved)

| # | Moat | Mechanism |
| --- | --- | --- |
| 1 | Data Flywheel | Every voice note makes CI smarter, battle cards sharper, benchmarks more precise. |
| 2 | Network Effect | Team Vault, team-vs-team challenges, coverage maps. |
| 3 | Methodology Moat | Jeff + Michael's combined credibility. Use in brand story — not as strategic defense. |

### From the Blitzkrieg plan (added)

| # | Moat | Mechanism |
| --- | --- | --- |
| 4 | IP Protection | Provisional patents on CI extraction method, Story Vault scoring algorithm. |
| 5 | Category Ownership | Own "Field Intelligence for Aesthetics" before anyone else claims it. |

### New — from the aesthetics pivot

| # | Moat | Mechanism |
| --- | --- | --- |
| 6 | Community Moat | AmSpa community density means StreetNotes word-of-mouth compounds inside a closed network. Once 10% of aesthetic reps use it, the other 90% hear about it from peers — not ads. |

Why six matters more than three Moats 1-3 are mechanism moats — product and founder. Moats 4-5 are defensive moats — legal and semantic. Moat 6 is an environmental moat — it only exists because the vertical is concentrated. Miss the vertical, and Moat 6 disappears.

# Part 4 — Metrics & Verification

Preserved from the moat plan — all correct. Only the target values shift to reflect the revised vertical.

## 4.1 — Leading and Lagging Indicators

| Phase | Leading Indicator | Lagging Indicator |
| --- | --- | --- |
| Phase 1 (months 0-6) | Founder conversations/week, /debrief emails/week | 100 paying reps in aesthetics. 80% 3-month retention. |
| Phase 2 (months 6-12) | Team seat ratio, dashboard MAU | 30 teams. Org-level deployment. NPS 50+. |
| Phase 3 (months 12-24) | New-user activation accuracy, cross-user feature adoption | 2,000 reps (across verticals). $3M ARR. |

## 4.2 — The Single Metric

REFERRAL RATE. If aesthetic reps are not telling other aesthetic reps, the moat is not forming. Every other metric lags this one.

## 4.3 — Moat Score Trajectory (revised for aesthetics)

| Milestone | Moat Plan Target | Aesthetics Revised | Rationale |
| --- | --- | --- | --- |
| Today | 3.5/10 | 3.5/10 | Starting position unchanged. |
| Month 6 | 5.0/10 | 5.5/10 | Concentrated community accelerates network effect. |
| Month 12 | 6.2/10 | 6.5/10 | Faster team lock-in in smaller market. |
| Month 18 | 7.3/10 | 7.5/10 | Stronger vertical dominance. |
| Month 24 | 7.5/10 | 8.0/10 if Gong has not entered | Gong won't — aesthetics is too niche for their ICP culture. |

## 4.4 — Risk Register

Four risks materially affect the revised plan. Each has a specific leading signal and a specific mitigation.

| Risk | Leading Signal | Mitigation |
| --- | --- | --- |
| Aesthetics referral rate stalls below 25% at Month 3 | Customer interviews surface "nice to have," not "can't work without" | Tighten ICP to injectables-only reps. Re-run concierge onboarding on failure segment. Do not add paid spend — paid cannot fix a referral problem. |
| Veeva accelerates aesthetics-adjacent push | Veeva marketing targets med-spa-proximate accounts; Vault CRM aesthetic vertical module announced | Pre-empt: publish the "State of Aesthetic Field Sales" report and lock category ownership of "Field Intelligence for Aesthetics" before Veeva can claim the category. |
| Gong enters aesthetics earlier than expected | Gong hires aesthetics vertical lead; Gong Engage markets to Allergan or Galderma | Low probability — aesthetics is too small for Gong's $250K ACV ICP. If it happens, position as "field intelligence" vs. their "call intelligence" — different buyer, different workflow. |
| Michael's Symplast network fails to convert to warm intros | First 10 intros do not produce 5+ discovery calls | Switch Michael's motion from brand VPs to 2-3 anchor MedSpa owners. Build bottoms-up credibility before going back to brand HQ. |

# Part 5 — Critical Files to Modify

Preserved from the moat plan, updated for aesthetics vocabulary and sequencing.

| Priority | Change | Phase |
| --- | --- | --- |
| 1 | Vertical-specific few-shot prompts for aesthetics (injectable brands, device brands, MedSpa terminology). | 0-30 days |
| 1 | CRM stage mapper for aesthetics deal stages. | 0-30 days |
| 1 | Competitor alias dictionary: Allergan, Galderma, Merz, Revance, Evolus, InMode, BTL, Cutera, Sciton, Candela, SkinMedica, SkinCeuticals, ZO, Alastin, Mentor, Natrelle, Motiva, Sientra. | 0-30 days |
| 2 | user_field_rules table + switching cost layer. | 30-60 days |
| 2 | /debrief rewritten for "Post-Visit Debrief for Aesthetic Sales Reps." | 30-60 days |
| 2 | Story Vault MVP with aesthetic content (ABT framework + Feel/Felt/Found for injector objections). | 30-90 days |
| 3 | Manager dashboard + team-vs-team Story Vault. | 60-180 days |
| 4 | Dynamic battle cards (Allergan vs Galderma vs Merz). | 120-180 days |
| 5 | Cross-user telemetry opt-in. | 180-240 days |

CLOSING

"The aesthetics vertical proves the model, proves retention, and proves community-led distribution. Every adjacent vertical after that is a copy-paste with vertical-specific vocabulary."

"Build for 5,000 reps. Own them. Then use that proof to detonate into 200,000."

StreetNotes.ai

Validated Strategy & Restructured GTM

April 2026  |  CONFIDENTIAL  |  Prepared for Jeff Meyers & Michael Hervis

SimilarWeb traffic data for Hey DAN (heydan.ai), monthly visit trend, https://www.similarweb.com/website/heydan.ai/

AmSpa Medical Spa Show attendance figures and event details, https://medicalspashow.com/